| PROJECT COVER SHEET – Updated 12/11/24 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Title/ Number: |  |  |  | GPIP Vessel Haul-Out Development – Phase 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Manager: |  | Michael Harmon |  |  |  |  |  |  |  |  |  | Project Sponsor: |  |  |  |  | Garry White |  |  |  |
| Project Description: |  |  | Planning, Environmental Permitting, Engineering Design, and CMAR Construction of Phase 1 Improvements including a 150-ton haul-out pier, wash-down pad, water treatment, and 150-ton boat hoist at Gary Paxton Industrial Park, Sitka, Alaska. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Design |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Construction |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Other |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Charter Available? |  |  |  |  | - Yes |  |  |  | - No |  |  |  |  |  |  |  |  |  |  |  |
| Project Status: (highlight green, yellow, red) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Scope |  |  |  |  |  |  | Schedule |  |  |  |  |  |  |  | Budget |  |  |  |  |  |
| Milestones: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Recently Completed - 04.26.23 Site No. 2 Selected by GPIP BOD - 07.25.23 Assembly Adopted Concept 4 - 01.15.24 Environmental Permit Applications - 03.01.24 35% Design Complete - 03.27.24 Award to WMC - 04.16.24 Travel Lift Bid (10-month delivery) - 04.18.24 WMC CMAR Contract Executed - 05.24.24 65% Design Complete - 07.02.24 Final Design & Fixed Construction Price - 11.21.24 Permits Acquired and Construction Start |  |  |  |  |  |  |  |  |  |  | Upcoming - GPIP/Assembly Meetings to discuss budget increase for concrete washdown - Q4 ’24 – Q1 ‘25: On Site Construction - Q1 ’25 Boat Hoist Delivery - Boatyard Operational: Q1 ‘25 |  |  |  |  |  |  |  |  |  |
| Project Budget: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Phase 1 - Estimated Total Project Cost |  |  |  |  |  |  |  |  |  |  |  | $9,781,040 |  |  |  |  |  |  |  |  |
| General Fund Working Capital |  |  |  |  |  |  |  |  |  |  |  | $8,444,565.00 |  |  |  |  |  |  |  |  |
| GPIP Working Capital |  |  |  |  |  |  |  |  |  |  |  | $350,000 |  |  |  |  |  |  |  |  |
| Grants |  |  |  |  |  |  |  |  |  |  |  | $1,000,000.00 |  |  |  |  |  |  |  |  |
| Other PSMFC |  |  |  |  |  |  |  |  |  |  |  | $336,475 |  |  |  |  |  |  |  |  |
|  | Total Funded |  |  |  |  |  |  |  |  |  |  | $10,131,040 |  |  |  |  |  |  |  |  |
| Phase 2 Funding Gap |  |  |  |  |  |  |  |  |  |  |  | $23,894,117 |  |  |  |  |  | GPIP Fund |  |  |
| Contract Management: (list all contracts anticipated on the project) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Contractor/Function* |  |  |  |  |  |  |  |  |  |  |  |  | Type** |  |  | Amount |  |  | % of Project |  |
| PND –Preconstruction, Permitting, Design & Const. Services |  |  |  |  |  |  |  |  |  |  |  |  | T&M/LS |  |  | $1,415,967 |  |  | 14% |  |
| Western Marine Construction (WMC) |  |  |  |  |  |  |  |  |  |  |  |  | CMAR |  |  | $6,179,362 |  |  | 61% |  |
| Kendrick Equipment (Marine Travelift Purchase) PND - Specialty Inspection Services (Future Procurement) CBS Indirect Cost & CBS Permits ($71k spent thru Aug.) Electrical Dept. Power Service (Future Procurement) WMC - Added Concrete Washdown Pad Current Construction Contingency |  |  |  |  |  |  |  |  |  |  |  |  | LS T&M Payroll T&M LS - |  |  | $1,377,800 $127,256 $149,282 $31,373 500,000 $350,000 |  |  | 14% 1.3% 1.5% 0.3% 5% 3% |  |
| 818 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| General Comments: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| The construction start was delayed due to federal permits not getting executed on the committed timeline by the agencies. Shipyard operations is not part of this project charter and are a separate development process. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Key Milestones:  12/11/24 UPDATE

| Key Tasks & Milestones | Start Date | End Date |
| --- | --- | --- |
| 1. Project Charter Approval: The Project Charter is brought to GPIP Board for approval. |  | 11/21/22 |
| 2. Project Budget Appropriation Assembly | 11/8/22 | 11/22/22 |
| 3. Prepare RFQ for PM services Port Planner SME | 11/17/22 | 12/8/22 |
| 4. Advertise PM/Port Planner RFQ | 12/12/22 | 2/1/23 |
| 5. Selection of PM/Port Planner/Engineer- PND | 2/2/23 | 3/6/23 |
| 6. Contract Execution/NTP for PM/Port Planner/Engineer | 3/7/23 | 3/29/23 |
| 7. Planning, Surveying, Public Involvement Process, Concepts, Costs, Preferred Alternative, Final Basis of Design & Charter Scope | 4/3/23 | 7/31/23 |
| 8. Geotechnical Invest. - Work Plan, Driller Contract, Drilling Permits, Fieldwork, Analyses & Geo Report | 5/22/23 | 01/31/24 |
| 9. Concept Rescoping due to Geotech Findings | 10/1/23 | 11/15/23 |
| 10. Biological Assessment, IHA & Environmental Permit Applications | 5/22/23 | 01/15/24 |
| 11. Regulatory Consultations, Permit Reviews and Authorizations | 7/15/23 | 11/21/24* |
| 12. 35% Preliminary Design | 11/15/23 | 3/1/24 |
| 13. Prepare CMAR RFP | 11/15/23 | 2/06/24 |
| 14. CMAR Solicitation & Contract Execution | 1/15/24 | 4/18/24 |
| 15. PND 65% Design Develop w/ WMC, CBS & GPIP | 4/01/24 | 5/24/24 |
| 16. WMC GMP Development | 4/01/24 | 6/3/24 |
| 17. Ph 1 Scope Refinement, Finalize GMP & WMC CO | 6/04/24 | 6/18/24 |
| 18. PND Final Design & Stamped Construction Docs | 6/18/24 | 7/16/24 |
| 19. Material Procurement | 6/18/24 | 12/1/24 |
| 20. On Site Construction | 11/21/24 | 3/30/25* |
| 21. Secure Operator for 2025 Season | 3/15/24 | 3/15/25* |
| 22. Procure 150T Boat Hoist | 12/1/23 | 3/15/25* |
| 23. Haul Out is Operational |  | 4/30/25 |
| * Critical Path Items- Environmental Permitting has delayed construction originally planned to start 10/15/24 |  |  |
| Milestones for Phase 2 TBD once funding is secured: |  |  |
| Need to masterplan uplands during the development of Phase 1 to apply for grants and position this phase to proceed. |  |  |
| Environmental permitting will likely need to be redone once this phase is better defined through a masterplan and funding is available. |  |  |