| PROJECT COVER SHEET – Updated September 16, 2024 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Title/ Number: |  |  |  | GPIP Vessel Haul-Out Development – Phase 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Manager: |  | Michael Harmon |  |  |  |  |  |  |  |  |  | Project Sponsor: |  |  |  |  | Garry White |  |  |  |
| Project Description: |  |  | Planning, Environmental Permitting, Engineering Design, and CMAR Construction of Phase 1 Improvements including a 150-ton haul-out pier, membrane wash-down pad, water treatment, and 150-ton boat hoist at Gary Paxton Industrial Park, Sitka, Alaska. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Design |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Construction |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Other |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Charter Available? |  |  |  |  | - Yes |  |  |  | - No |  |  |  |  |  |  |  |  |  |  |  |
| Project Status: (highlight green, yellow, red) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Scope |  |  |  |  |  |  | Schedule |  |  |  |  |  |  |  | Budget |  |  |  |  |  |
| Milestones: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Recently Completed - 04.26.23 Site No. 2 Selected by GPIP BOD - 07.25.23 Assembly Adopted Concept 4 - 01.15.24 Environmental Permit Applications - 03.01.24 35% Design Complete - 03.27.24 Award to WMC - 04.16.24 Travel Lift Bid (10-month delivery) - 04.18.24 WMC CMAR Contract Executed - 05.24.24 65% Design Complete - 06.03.24 WMC GMP Pricing submitted - 07.02.24 Final Design & Fixed Construction Price |  |  |  |  |  |  |  |  |  |  | Upcoming - GPIP/Assembly Meetings to discuss budget increase for concrete washdown - Q4 ‘24: Final Regulatory Review - Q2-4 ‘24: Material Procurement - Q4 ’24 – Q1 ‘25: On Site Construction - Q1 ’25 Boat Hoist Delivery - Boatyard Operational: Q1 ‘25 |  |  |  |  |  |  |  |  |  |
| Project Budget: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Phase 1 - Estimated Total Project Cost |  |  |  |  |  |  |  |  |  |  |  | $9,281.040 |  |  |  |  |  |  |  |  |
| Working Capital |  |  |  |  |  |  |  |  |  |  |  | $8,281,040.00 |  |  |  |  |  |  |  |  |
| Loans |  |  |  |  |  |  |  |  |  |  |  | $0.00 |  |  |  |  |  |  |  |  |
| Grants |  |  |  |  |  |  |  |  |  |  |  | $1,000,000.00 |  |  |  |  |  |  |  |  |
| Other |  |  |  |  |  |  |  |  |  |  |  | $0.00 |  |  |  |  |  |  |  |  |
|  | Total Funded |  |  |  |  |  |  |  |  |  |  | $9,281,040 |  |  |  |  |  |  |  |  |
| Phase 2 Funding Gap |  |  |  |  |  |  |  |  |  |  |  | $23,894,117 |  |  |  |  |  |  |  |  |
| Contract Management: (list all contracts anticipated on the project) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Contractor/Function* |  |  |  |  |  |  |  |  |  |  |  |  | Type** |  |  | Amount |  |  | % of Project |  |
| PND –Preconstruction, Permitting, Design & Const. Services |  |  |  |  |  |  |  |  |  |  |  |  | T&M/LS |  |  | $1,415,967 |  |  | 15% |  |
| Western Marine Construction (WMC) & Project Contingency |  |  |  |  |  |  |  |  |  |  |  |  | CMAR |  |  | $6,179,362 |  |  | 67% |  |
| Travel Hoist Purchase Specialty Inspection Services (Future Procurement) CBS Indirect Cost & CBS Permits ($71k spent thru Aug.) Electrical Dept. Power Service (Future Procurement) Current Construction Contingency Remaining |  |  |  |  |  |  |  |  |  |  |  |  | LS T&M Payroll T&M - |  |  | $1,377,800 $126,538 $150,000 $31,373 $0 |  |  | 15% 0.3% 1.6% 0.3% 0% |  |
| 818 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| General Comments: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| The scope had to be reduced due to unexpected pile depths and the budget remains short for the full scope. Shipyard operations is not part of this project charter and are a separate development process. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Key Milestones:  November 15, 2024 UPDATE

| Key Tasks & Milestones | Start Date | End Date |
| --- | --- | --- |
| 1. Project Charter Approval: The Project Charter is brought to GPIP Board for approval. |  | 11/21/22 |
| 2. Project Budget Appropriation Assembly | 11/8/22 | 11/22/22 |
| 3. Prepare RFQ for PM services Port Planner SME | 11/17/22 | 12/8/22 |
| 4. Advertise PM/Port Planner RFQ | 12/12/22 | 2/1/23 |
| 5. Selection of PM/Port Planner/Engineer- PND | 2/2/23 | 3/6/23 |
| 6. Contract Execution/NTP for PM/Port Planner/Engineer | 3/7/23 | 3/29/23 |
| 7. Planning, Surveying, Public Involvement Process, Concepts, Costs, Preferred Alternative, Final Basis of Design & Charter Scope | 4/3/23 | 7/31/23 |
| 8. Geotechnical Invest. - Work Plan, Driller Contract, Drilling Permits, Fieldwork, Analyses & Geo Report | 5/22/23 | 01/31/24 |
| 9. Concept Rescoping due to Geotech Findings | 10/1/23 | 11/15/23 |
| 10. Biological Assessment, IHA & Environmental Permit Applications | 5/22/23 | 01/15/24 |
| 11. Regulatory Consultations, Permit Reviews and Authorizations | 7/15/23 | 11/21/24* |
| 12. 35% Preliminary Design | 11/15/23 | 3/1/24 |
| 13. Prepare CMAR RFP | 11/15/23 | 2/06/24 |
| 14. CMAR Solicitation & Contract Execution | 1/15/24 | 4/18/24 |
| 15. PND 65% Design Develop w/ WMC, CBS & GPIP | 4/01/24 | 5/24/24 |
| 16. WMC GMP Development | 4/01/24 | 6/3/24 |
| 17. Ph 1 Scope Refinement, Finalize GMP & WMC CO | 6/04/24 | 6/18/24 |
| 18. PND Final Design & Stamped Construction Docs | 6/18/24 | 7/16/24 |
| 19. Material Procurement | 6/18/24 | 12/1/24 |
| 20. On Site Construction | 11/21/24 | 3/15/25* |
| 21. Secure Operator for 2025 Season | 3/15/24 | 3/15/25* |
| 22. Procure 150T Boat Hoist | 12/1/23 | 2/15/25* |
| 23. Haul Out is Operational |  | 3/15/25 |
| * Critical Path Items- Environmental Permitting has delayed construction originally planned to start 10/15/24 |  |  |
| Milestones for Phase 2 TBD once funding is secured: |  |  |
| Need to masterplan uplands during the development of Phase 1 to apply for grants and position this phase to proceed. |  |  |
| Environmental permitting will likely need to be redone once this phase is better defined through a masterplan and funding is available. |  |  |