| PROJECT COVER SHEET – Updated July 16, 2024 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Title/ Number: |  |  |  | GPIP Vessel Haul-Out Development – Phase 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Manager: |  | Michael Harmon |  |  |  |  |  |  |  |  |  | Project Sponsor: |  |  |  |  | Garry White |  |  |  |
| Project Description: |  |  | Planning, Environmental Permitting, Engineering Design and CMAR Construction of Phase 1 Improvements including a 150-Ton Boat Haul-Out Pier, Wash Down Pad, North Boat Yard and 150T Boat Hoist at Gary Paxton Industrial Park, Sitka, Alaska. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Design |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Construction |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Other |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Charter Available? |  |  |  |  | - Yes |  |  |  | - No |  |  |  |  |  |  |  |  |  |  |  |
| Project Status: (highlight green, yellow, red) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Scope |  |  |  |  |  |  | Schedule |  |  |  |  |  |  |  | Budget |  |  |  |  |  |
| Milestones: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Recently Completed - 04.26.23 Site No. 2 Selected by GPIP BOD - 06.22.23 GPIP BOD adopted Concept 4 - 07.25.23 Assembly Adopted Concept 4 - 09.29.23 Geotech Field Investigation Complete - 01.15.24 Environmental Permit Applications - 03.01.24 35% Design Complete - 03.27.24 Award to WMC - 04.16.24 Travel Lift Bid (10-month delivery) - 04.18.24 WMC CMAR Contract Executed - 05.24.24 65% Design Complete - 06.03.24 WMC GMP Pricing submitted - 07.02.24 Final Design and Construction Pricing |  |  |  |  |  |  |  |  |  |  | Upcoming - GPIP Board Meeting project price/scope update and operational RFQ – July 18, 2024 - Q 3 ‘24: Final Construction Price Amendment & Regulatory Review - Q2-4 ‘24: Material Procurement - Q4 ’24 – Q1 ‘25: On Site Construction - Q1 ’25 Boat Hoist Delivery - Boatyard Operational: Q1 ‘25 |  |  |  |  |  |  |  |  |  |
| Project Budget: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Phase 1 - Estimated Total Project Cost |  |  |  |  |  |  |  |  |  |  |  | $9,281.040 |  |  |  |  |  |  |  |  |
| Working Capital |  |  |  |  |  |  |  |  |  |  |  | $8,281,040.00 |  |  |  |  |  |  |  |  |
| Loans |  |  |  |  |  |  |  |  |  |  |  | $0.00 |  |  |  |  |  |  |  |  |
| Grants |  |  |  |  |  |  |  |  |  |  |  | $1,000,000.00 |  |  |  |  |  |  |  |  |
| Other |  |  |  |  |  |  |  |  |  |  |  | $0.00 |  |  |  |  |  |  |  |  |
|  | Total Funded |  |  |  |  |  |  |  |  |  |  | $9,281,040 |  |  |  |  |  |  |  |  |
| Phase 2 Funding Gap |  |  |  |  |  |  |  |  |  |  |  | $23,894,117 |  |  |  |  |  |  |  |  |
| Contract Management: (list all contracts anticipated on the project) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Contractor/Function* |  |  |  |  |  |  |  |  |  |  |  |  | Type** |  |  | Amount |  |  | % of Project |  |
| PND – Preconstruction, Permitting and Design Services |  |  |  |  |  |  |  |  |  |  |  |  | T&M |  |  | $1,347,537 |  |  | 14% |  |
| Western Marine Construction (WMC) & Project Contingency |  |  |  |  |  |  |  |  |  |  |  |  | CMAR |  |  | $6,279,362 |  |  | 68% |  |
| Travel Hoist Purchase Construction Management & CBS Indirect Cost |  |  |  |  |  |  |  |  |  |  |  |  | LS T&M |  |  | $1,377,800 $276,341 |  |  | 15% 3% |  |
| 818 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| General Comments: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| The scope had to be reduced due to unexpected pile depths and the budget remains short for the full scope. Shipyard operations is not part of this project charter and are a separate development process. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Key Milestones:  June 4, 2024 UPDATE

| Key Tasks & Milestones | Start Date | End Date |
| --- | --- | --- |
| 1. Project Charter Approval: The Project Charter is brought to GPIP Board for approval. |  | 11/21/22 |
| 2. Project Budget Appropriation Assembly | 11/8/22 | 11/22/22 |
| 3. Prepare RFQ for PM services Port Planner SME | 11/17/22 | 12/8/22 |
| 4. Advertise PM/Port Planner RFQ | 12/12/22 | 2/1/23 |
| 5. Selection of PM/Port Planner/Engineer- PND | 2/2/23 | 3/6/23 |
| 6. Contract Execution/NTP for PM/Port Planner/Engineer | 3/7/23 | 3/29/23 |
| 7. Planning, Surveying, Public Involvement Process, Concepts, Costs, Preferred Alternative, Final Basis of Design & Charter Scope | 4/3/23 | 7/31/23 |
| 8. Geotechnical Invest. - Work Plan, Driller Contract, Drilling Permits, Fieldwork, Analyses & Geo Report | 5/22/23 | 01/31/24 |
| 9. Concept Rescoping due to Geotech Findings | 10/1/23 | 11/15/23 |
| 10. Biological Assessment, IHA & Environmental Permit Applications | 5/22/23 | 01/15/24 |
| 11. Regulatory Consultations, Permit Reviews and Authorizations | 7/15/23 | 10/15/24* |
| 12. 35% Preliminary Design | 11/15/23 | 3/1/24 |
| 13. Prepare CMAR RFP | 11/15/23 | 2/06/24 |
| 14. CMAR Solicitation & Contract Execution | 1/15/24 | 4/18/24 |
| 15. PND 65% Design Develop w/ WMC, CBS & GPIP | 4/01/24 | 5/24/24* |
| 16. WMC GMP Development | 4/01/24 | 6/3/24 |
| 17. Ph 1 Scope Refinement, Finalize GMP & WMC CO | 6/04/24 | 6/18/24 |
| 18. PND Final Design & Stamped Construction Docs | 6/18/24 | 7/16/24 |
| 19. Material Procurement | 6/18/24 | 12/1/24 |
| 20. On Site Construction | 10/15/24 | 3/15/25* |
| 21. Secure Operator for 2025 Season | 3/15/24 | 3/15/25* |
| 22. Procure 150T Boat Hoist | 12/1/23 | 2/15/25* |
| 23. Haul Out is Operational |  | 3/15/25 |
| * Critical Path Items |  |  |
| Milestones for Phase 2 TBD once funding is secured: |  |  |
| Need to masterplan uplands during the development of Phase 1 to apply for grants and position this phase to proceed. |  |  |
| Environmental permitting will likely need to be redone once this phase is better defined through a masterplan and funding is available. |  |  |